## Slide 1: Direct Payments Review of Administration Policies and Procedures 2016
Knowsley MBC
Our Approach
Lynn.anders@knowsley.gov.uk

## Slide 2: Project Groups
Approach – Develop a robust KMBC policy for the administration, control and monitoring of direct payments for clients choosing to take personal budgets by DP
How – develop and implement procedures and controls that the Council will use to ensure that practitioners, clients and budget holders have adequate assurance that DP’s are calculated and recorded correctly, expenditure is evidenced, support plan outcomes are being met.

## Slide 3: Examples of Findings
Issue/Effect | Cause
Confusion around direct payment and procedures to be followed DP managed by inappropriate person | No Policy, lack of standard processes, lack of guidance for client and practitioners Workarounds allowed in systems Lack of client checks
Practitioners unable to reconcile previous payments during review Payments not calculated correctly – over and under Transition client challenge change in rates | Cost Calculator not fit for purpose No standard Rates across the services PA rates not equitable re employer costs Breakdown of hours and rates not recorded sufficiently
DP’s not used correctly Managed account provider is not able to verify payments and hours Overdrawn accounts Non payment of client contributions | Lack of responsibility by client Vague agreements Support plans not detailed enough Tasks completed to meet outcomes not recorded Lack of monitoring and control to support Audit.
Unable to identify rates for analysis and forecasting uplifts etc. | DP not sufficiently broken down in system where payment is generated Various payments rolled up into hourly rates No standard rates

## Slide 4: Progress
Draft policy at final stages for approval – clear policy for the administration of direct payments. Includes reference to checks on nominated persons.
Client guidance – supports the advice and guidance contract with third party but is clear for both on what the process is and what DP’s can be used for. Clarifies client responsibility around evidence of expenditure, recording of tasks to meet outcomes, signing time sheets, selecting managed account providers
Client Agreement – in draft with legal but includes declaration by client and/or nominated persons
Practitioner Guidance – aligned to all of the above.

## Slide 5: Progress so far
Standard rates – calculated and ready for approval
PA costs – hourly rate and annual employer costs are calculated separately to meet HMRC standards and remove inequity in calculation of employer costs
Changes to system recording – details of hours and rate used to be recorded, outcomes recorded, starter forms redesigned to remove ambiguity, payment elements in SWIFT to allow a breakdown of total payment to remove confusion and allow future uplifts to be applied accurately, improved analysis.
Communication to clients – to be agreed – changes to current PA rates, changes to calculation of PA rates, pensions impact,
Task Sheets, electronic submission of evidence
Partnership agreement for providers of managed accounts
Make system changes – any that are still to be approved.

## Slide 6: How will things change for Practitioners and Clients
Clear policy and guidance
What you record – high level not detailed but sufficient to address issues we currently find
How you will record – system changes – minor
DP calculation – improved cost calculator and breakdown of total payment recorded
Standard rates to apply
Outcomes evidenced (high level records maintained by PA or Agency worker) to enable review of current payment against outcomes in the support plans
Improved monitoring of DP’s to avoid clients reaching crisis point
Client will have improved understanding leading to reduction in queries and complaints,
Responsibility of client is documented and agreed.